## Sheet1
Tool | Issue ID | Description | Reporter | Assignee | Estimated Hours | Impact | Link | Presented to TRB | TRB Decision | Bug Report Date | Bug Resolution Date | Severity | Comment
caGrid Security | CAGRID-540 | SHA 2 support |  |  | 2-3 months of work remain | A NIST mandate requires all federal systems with issue or otherwise work with SSL certificates to use SHA 2 (or better) by 12/31/2010. The mandate contains a proviso for legacy systems to obtain an extension, which we have through 12/31/2011 | https://jira.citih.osumc.edu/browse/CAGRID-540 | 03/29/11 | TBD |  | TBD | Blocker | We've been working on this since late last year. Great progress has been made, and we're reasonably sure of the functionality. THESE CHANGES WILL BREAK BACKWARDS COMPATIBILITY WITH ALL SECURE CAGRID 1.X SERVICES. A COMMUNITY ANNOUNCEMENT MUST BE ISSUED TO ADDRESS THIS IMPACT ON ALL USES OF CAGRID. THE DEV TEAM DRAFTED SUCH A COMMUNIQUE ON 10/22/2010, HOWEVER THE ENTERPRISE SECURITY TEAM HAS ASSERTED AUTHORITY OVER SUCH A MESSAGE. IN AN EFFORT TO AVOID FURTHER DELAYS, AN ISSUE HAS BEEN CREATED IN THE EST TRACKER HERE: https://tracker.nci.nih.gov/browse/CSS-4
caGrid Data Services | CAGRID-537 | Support caCORE SDK 4.4 in caGrid Data Services in caGrid 1.4 and 1.3 |  |  | 2-3 weeks of work and testing, total, approx 2 weeks remaining | Users moving to the newest version of the caCORE SDK need to be able to create caGrid data services using their SDK system as a backend. Without this extension, that's not possible. | https://jira.citih.osumc.edu/browse/CAGRID-537 | 03/29/11 | TBD |  | TBD | High / Enhancement | This can be done post release of caGrid 1.4 as an extension to the Introduce toolkit that users can download throught the existing update functionality.
caGrid Federated Query Processor | CAGRID-646 | Federated Query Processor improvements to performance and scalability |  |  | 2 weeks | FQP should be improved to better handle very large query results and joins. | https://jira.citih.osumc.edu/browse/CAGRID-646 | 03/29/11 | TBD |  | TBD | High / Enhancement | The University of Alabama Birmingham has already done a good deal of this work and is creating a caGrid community project for their enhanced FQP. We should pull those improvements into the main codebase so they can be better supported and leveraged by anyone using caGrid.
caGrid Core | CAGRID-104 | Support deploying grid services to Tomcat 6 and Jboss 5 |  |  | 2 weeks (possiby more if investigation reveals large changes required to integration tests) | The NCI tech stack calls for Tomcat 6 and JBoss 5. We may have to make some changes to the way Globus is deployed to fully support this. | https://jira.citih.osumc.edu/browse/CAGRID-104 | 03/29/11 | TBD |  | TBD | Normal / Enhancement | Both of these see strong adoption in the user community, and should be supported.
caGrid Core | CAGRID-161 | Fix caGrid builds when the path contains spaces |  |  | 2 weeks | caGrid doesn't build if the path contains spaces (i.e. c:/Documents and Settings/cagrid doesn't work) | https://jira.citih.osumc.edu/browse/CAGRID-161 | 03/29/11 | TBD |  | TBD | Normal
caGrid Introduce | CAGRID-304, CAGRID-641 | Long classpaths generated by Ant during startup of Introduce cause failures on Windows platforms. Introduce cannot be executed if it's in a deeply nested or otherwise long path location. |  |  | 1 week (mostly testing) | Users on the Windows OS will need to manually move Introduce to a location with a less verbose path; this may just be a band-aid since adding more extensions to Introduce will increase the classpath further. | https://jira.citih.osumc.edu/browse/CAGRID-304, https://jira.citih.osumc.edu/browse/CAGRID-631 | 2011-04-04 | TBD |  | TBD | High
caGrid Introduce / caGrid Core Services | CAGRID-597 | Introduce generated clients don't provide an obvious way to set the timeout when communicating with a remote service. The default of 60s is not sufficient for users with long-running jobs (UAB's FQP use case) |  |  | 1 day (upgraders, mostly) | The client code can be manually edited to facilitate setting the timeout, but users of the clent APIs in Jar format won't have this option. | https://jira.citih.osumc.edu/browse/CAGRID-597 | 2011-04-04 | TBD |  | TBD | Low | The template that generates the client code should be trivial to update, but the upgrade tools to bring an existing service up to the latest version will need some attention to get this right.
caGrid Dorian | caGrid-635 | Currently, when a user is inactivated their host certificates are placed on the CRL but they remain in active status. This is misleading and does not match the documentation. When user account is inactivated a. place associated host certs on CRL b. update associated host certs to "Suspended" When user account is deleted a. place associated host certs on CRL b. update associated host certs to "Compromised" |  |  | 3 Days | This was the source of a lot of confusion and frustration when a person who was registered as the "owner" of several core service host certificates left. That person's account in Dorian was disabled, and that caused the host certs for all the core services to be marked as revoked in the CRL, but still say "Active" in the DB and the GAARDS-UI. | https://jira.citih.osumc.edu/browse/CAGRID-635 | 2011-04-04 | TBD |  | TBD | High
caGrid Introduce |  | Upgraders for caGrid 1.3 and 1.4 to 1.5 need to be written so users can easily adopt the new release of caGrid |  |  | 1 week | caGrid provides backwards compatibility and upgradability for two versions previous. To facilitate this, the Introduce toolkit can perform the upgrades from old to the new version of services. The code for this needs to be written. | https://jira.citih.osumc.edu/browse/CAGRID-594, others | 2011-04-04 | TBD |  | TBD | High | Only new features, schema changes, model changes, etc need to be rolled in by the upgraders. This will actually be ongoing effort throughout the development cycle depending on what changes are made that require an upgrade. We can probably add subtasks for those specific items as we encounter them
caGrid Core | CAGRID-652 | caGrid should support building and execution on the openJDK JVM |  |  | 1 week | The recent rifting in the Java community has lead to many users opting to use openJDK instead of the Oracle / Sun JDK. Additionally, CentOS, a common deployment platform, includes openJDK out of the box. | https://jira.citih.osumc.edu/browse/CAGRID-652 | 2011-04-04 | TBD |  | TBD | Normal | Initial, and mostly accidental, investigation indicates that this almost works anyway. We know of a major problem with serialization returning no data from caCORE SDK backed data services. It remains to be seen if this is an SDK bug, or something we can actually fix.