## Sheet1
Tool | Issue ID | Description | Reporter | Assignee | Estimated Hours | Impact | Link | Presented to TRB | TRB Decision | Bug Report Date | Bug Resolution Date | Severity | Comment
caGrid Security | CAGRID-540 | SHA 2 support |  |  | 2-3 months of work remain | A NIST mandate requires all federal systems with issue or otherwise work with SSL certificates to use SHA 2 (or better) by 12/31/2010. The mandate contains a proviso for legacy systems to obtain an extension, which we have through 12/31/2011 | https://jira.citih.osumc.edu/browse/CAGRID-540 | 03/29/11 | TBD |  | TBD | ASTRONOMICAL | We've been working on this since late last year. Great progress has been made, and we're reasonably sure of the functionality. THESE CHANGES WILL BREAK BACKWARDS COMPATIBILITY WITH ALL SECURE CAGRID 1.X SERVICES. A COMMUNITY ANNOUNCEMENT MUST BE ISSUED TO ADDRESS THIS IMPACT ON ALL USES OF CAGRID. THE DEV TEAM DRAFTED SUCH A COMMUNIQUE ON 10/22/2010, HOWEVER THE ENTERPRISE SECURITY TEAM HAS ASSERTED AUTHORITY OVER SUCH A MESSAGE. IN AN EFFORT TO AVOID FURTHER DELAYS, AN ISSUE HAS BEEN CREATED IN THE EST TRACKER HERE: https://tracker.nci.nih.gov/browse/CSS-4
caGrid Data Services | CAGRID-537 | Support caCORE SDK 4.4 in caGrid Data Services in caGrid 1.4 and 1.3 |  |  | 2-3 weeks of work and testing | Users moving to the newest version of the caCORE SDK need to be able to create caGrid data services using their SDK system as a backend. Without this extension, that's not possible. | https://jira.citih.osumc.edu/browse/CAGRID-537 | 03/29/11 | TBD |  | TBD | High / Enhancement | This can be done post release of caGrid 1.4 as an extension to the Introduce toolkit that users can download throught the existing update functionality.
caGrid Federated Query Processor | CAGRID-646 | Federated Query Processor improvements to performance and scalability |  |  | 2 weeks | FQP should be improved to better handle very large query results and joins. | https://jira.citih.osumc.edu/browse/CAGRID-646 | 03/29/11 | TBD |  | TBD | High / Enhancement | The University of Alabama Birmingham has already done a good deal of this work and is creating a caGrid community project for their enhanced FQP. We should pull those improvements into the main codebase so they can be better supported and leveraged by anyone using caGrid.
caGrid Core | CAGRID-104 | Support deploying grid services to Tomcat 6 and Jboss 5 |  |  | 2 weeks (possiby more if investigation reveals large changes required to integration tests) | The NCI tech stack calls for Tomcat 6 and JBoss 5. We may have to make some changes to the way Globus is deployed to fully support this. | https://jira.citih.osumc.edu/browse/CAGRID-104 | 03/29/11 | TBD |  | TBD | Normal / Enhancement | Both of these see strong adoption in the user community, and should be supported.
caGrid Core | CAGRID-161 | Fix caGrid builds when the path contains spaces |  |  | 2 weeks | caGrid doesn't build if the path contains spaces (i.e. c:/Documents and Settings/cagrid doesn't work) | https://jira.citih.osumc.edu/browse/CAGRID-161 | 03/29/11 | TBD |  | TBD | Normal