## caGrid-1-4.csv
Nr | Title | Duration | Percent Complete | Notes
1 | caGrid 1.4 Development |  | 7% | https://gforge.nci.nih.gov/pm/task.php?group_project_id=1205&group_id=25&func=browse
2 | Start
3 | Bug Fixes |  | 19% | https://gforge.nci.nih.gov/pm/task.php?func=detailtask&project_task_id=3045&group_id=25&group_project_id=1205
4 | Start
5 | Introduce generated WSDL breaks unique key contraint of WSDL XSD |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=19045&group_id=25&atid=174
6 | Introduce is not passing any system properties on to it's ant calls it makes when running the engine. |  | 0% | https://gforge.nci.nih.gov/tracker/?group_id=25&atid=174&func=detail&aid=9466
7 | Introduce creates cycles between sub-context's resource base and main service's config class |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=16898&group_id=25&atid=174
8 | Introduce add/remove types panel hides some interface components at low resolutions |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22795&group_id=25&atid=174
9 | Introduce grid service path cannot contain spaces |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=19306&group_id=25&atid=174
10 | Introduce add/remove types schema file selection bug |  |  | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22804&group_id=25&atid=174
11 | Introduce disallows hyphenated last names for Point of Contact |  |  | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22096&group_id=25&atid=174
12 | Introduce GUI can be used to add multiple exceptions of the same type to operations |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22515&group_id=25&atid=174
13 | Introduce-generated services create EPRs with an incorrect hostname |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22308&group_id=25&atid=174
14 | Infinite loop in Introduce updater |  |  | https://gforge.nci.nih.gov/tracker/?func=detail&aid=21065&group_id=25&atid=174
15 | \Multiple GAARDS documentation pages reference the \"\"ui\"\" target of projects which no longer exists\"" |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=15609&group_id=25&atid=174
16 | GAARDS UI does not display the 'Set As Default' button after authenticating |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22807&group_id=25&atid=174
17 | GAARDS generates error if certificate is not selected for viewing |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=15611&group_id=25&atid=174
18 | Delegated Credential Types schema cannot be added to services via Introduce GUI |  |  | https://gforge.nci.nih.gov/tracker/?func=detail&aid=17666&group_id=25&atid=174
19 | Installer overwrites the installed credentials if already installed credentials are selected |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=20196&group_id=25&atid=174
20 | caGrid installer doesn't check Apache Tomcat version properly on Windows |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22275&group_id=25&atid=174
21 | Incorrect exception handling when deleting non-existant file |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=20375&group_id=25&atid=174
22 | connector redirect ports are not set to correct value when using custom https port |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22815&group_id=25&atid=174
23 | The Transfer service intermittently and randomly loses callbacks on transfer contexts |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22321&group_id=25&atid=174
24 | Missing XML prolog on schemas causes SyncGTS exception in JBoss |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22891&group_id=25&atid=174
25 | secure service deployed on port 443 has a connect bug (connects to port 8443) |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=23120&group_id=25&atid=174
26 | \Cannot select update patch after clicking \"\"Look for Updates\"\" for custom update site\"" |  | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=20679&group_id=25&atid=174
27 | SDK41QueryProcessor does not set the password for non-static logins |  |  | https://gforge.nci.nih.gov/tracker/?func=detail&aid=23252&group_id=25&atid=174
28 | websso packages sync description file | 0.75 days | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=20171&group_id=25&atid=174
30 | webSSO login does not work with CBIIT Authentication service | 1.5 days | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=22830&group_id=25&atid=174
32 | WebSSO not allowing AuthenticationProviders urls may be null | 0.75 days | 0% | https://gforge.nci.nih.gov/tracker/?func=detail&aid=20774&group_id=25&atid=174
34 | Finish |  | 0%
35 | Continuous Innovation |  | 0% | https://gforge.nci.nih.gov/pm/task.php?func=detailtask&project_task_id=3056&group_id=25&group_project_id=1205
36 | Start |  | 0%
37 | Ability to Display Current Target Grid Information |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=19379&group_id=25&atid=2252
38 | Installer should Allow full directory browsing |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20099&group_id=25&atid=2252
39 | Add support to resource property helper for client side authorization |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20237&group_id=25&atid=2252
40 | Make gov.nih.nci.cagrid.common.FaultHelper more usable |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20322&group_id=25&atid=2252
41 | Finish |  | 0%
42 | Data Services |  | 0% | https://gforge.nci.nih.gov/pm/task.php?func=detailtask&project_task_id=3046&group_id=25&group_project_id=1205
43 | Start |  | 0%
44 | CQL - allow subclass specification |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20228&group_id=25&atid=2252
46 | Implementation of Common Testing between Grid and SDK |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20221&group_id=25&atid=2252
48 | Proxy Framework and XML serialization integration in Grid Service |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20220&group_id=25&atid=2252
50 | XMI Reader API Integration in Introduce |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20217&group_id=25&atid=2252
52 | DCQL (FQP) should support query modifiers |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=19997&group_id=25&atid=2252
54 | Investigate adding support for processing abstract types in both query and return |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=19994&group_id=25&atid=2252
56 | CQL/DCQL does not allow associations to target object to be returned |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=19992&group_id=25&atid=2252
58 | Specify additional allowable CQL Predicate value datatypes |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=19990&group_id=25&atid=2252
60 | Conditions on aggregate data |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=19268&group_id=25&atid=2252
62 | Backport CQL2 association traversal logic to CQL1 |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=23740&group_id=25&atid=2252
64 | CQL 2.0 |  | 0%
66 | Design DCQL 2.0 |  | 0%
68 | Design FQP Engine to Implement DCQL 2.0 |  | 0%
70 | Implement DCQL 2.0 in FQP |  | 0%
72 | Finish |  | 0%
73 | Upgrade FQP Service to Introduce 1.4 |  | 0%
74 | Metadata Infrastructure |  | 0% | https://gforge.nci.nih.gov/pm/task.php?func=detailtask&project_task_id=3054&group_id=25&group_project_id=1205
75 | Start |  | 0%
76 | GME should provide a validate capability to validate a given XML document conforms to schemas that are stored in the GME |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20190&group_id=25&atid=2252
77 | Scott Oster |  | 0%
78 | Upgrade GME Service to Introduce 1.4 |  | 0%
79 | Upgrade MMS Service to Introduce 1.4 |  | 0%
80 | Finish |  | 0%
81 | Security Infrastructure |  | 0% | https://gforge.nci.nih.gov/pm/task.php?func=detailtask&project_task_id=3051&group_id=25&group_project_id=1205
82 | Start |  | 0%
83 | SyncGTS needs to use service property for sync description |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20087&group_id=25&atid=2252
85 | GridGrouper should provide a way for a user to request to be added to a (non-opt in) group |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20182&group_id=25&atid=2252
87 | Upgrade Dorian Service to Introduce 1.4 |  | 0%
88 | Implement support for managing host agreements |  | 0%
89 | Add support to GAARDS-UI for viewing and signing host agreements |  | 0% | 88
90 | Upgrade CDS Service to Introduce 1.4 |  | 0%
91 | Upgrade GridGrouper Service to Introduce 1.4 |  | 0%
92 | Upgrade GTS Service to Introduce 1.4 |  | 0%
93 | Upgrade Authentication Service to Introduce 1.4 |  | 0%
94 | Dorian should validate emails for new registrations |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20763&group_id=25&atid=2252
96 | Finish |  | 0%
97 | WebSSO |  | 0% | https://gforge.nci.nih.gov/pm/task.php?func=detailtask&project_task_id=3055&group_id=25&group_project_id=1205
98 | Start |  | 0%
99 | Document UI changes to ja-sig CAS |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20229&group_id=25&atid=2252
101 | Enhance logging in websso modules |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20401&group_id=25&atid=2252
103 | Logout filter should not need delegation EPR |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20411&group_id=25&atid=2252
105 | prototype on Shibboleth |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=21125&group_id=25&atid=2252
107 | Websso ivy artifacts should be more granular |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=22958&group_id=25&atid=2252
109 | Finish |  | 0%
110 | Workflow |  | 0% | https://gforge.nci.nih.gov/pm/task.php?func=detailtask&project_task_id=3052&group_id=25&group_project_id=1205
111 | Start |  | 0%
112 | Upgrade Taverna Service to Introduce 1.4 |  | 0%
113 | Upgrade BPEL Service to Introduce 1.4 |  | 0%
114 | Need workflow integration tests |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20090&group_id=25&atid=2252
115 | BPEL workflow should support CDS integration |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=23472&group_id=25&atid=2252
116 | Taverna workflow should support CDS integration |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=23473&group_id=25&atid=2252
117 | Finish |  | 0%
118 | Service Development Infrastructure |  | 0% | https://gforge.nci.nih.gov/pm/task.php?func=detailtask&project_task_id=3053&group_id=25&group_project_id=1205
119 | Start |  | 0%
120 | Transfer Service Needs Standard Metadata |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20224&group_id=25&atid=2252
122 | caGrid Transfer should have its data model registered in caDSR |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=20225&group_id=25&atid=2252
124 | Pass the ServiceInformation object into the NamespaceTypeDiscoveryComponent class |  | 0% | https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=21615&group_id=25&atid=2252
126 | Stabilize Introduce 1.4 |  | 0%
128 | Finish |  | 0%
129 | Code Freeze |  | 0%
130 | Finish |  | 0%