## tracker_report-2009-08(4).csv
artifact_id | summary | open_date | priority | assigned_to_name | submitter_name | last_modified_date | Affected Version | Severity | Resolution | Component | Target
22830 | webSSO login does not work with CBIIT Authentication service | 2009-08-12 20:00 | 5 | Santhosh Garmilla | Manav Kher | 2009-08-12 20:00 | HEAD | critical | None | WebSSO | 1.3/1.4
22815 | connector redirect ports are not set to correct value when using custom https port | 2009-08-11 20:14 | 3 | Nobody | William Stephens | 2009-08-11 20:14 | v1.3 | normal | None | Installer | 1.3/1.4
22807 | GAARDS UI does not display the 'Set As Default' button after authenticating | 2009-08-11 14:18 | 3 | Nobody | Himanshu Rathod | 2009-08-11 14:18 | v1.2 | normal | None | Other | 1.4
22804 | Introduce add/remove types schema file selection bug | 2009-08-11 09:55 | 3 | Shannon Hastings | Justin Permar | 2009-08-11 09:55 | v1.3 | None | None | Introduce | 1.4
22795 | Introduce add/remove types panel hides some interface components at low resolutions | 2009-08-10 19:04 | 3 | Shannon Hastings | Justin Permar | 2009-08-10 19:04 | v1.3 | None | None | Introduce | 1.4
22792 | Introduce updater creates empty directories in INTRODUCE_HOME | 2009-08-10 14:21 | 2 | Shannon Hastings | William Stephens | 2009-08-10 14:21 | None | minor | None | Introduce | 1.4
22515 | Introduce GUI can be used to add multiple exceptions of the same type to operations | 2009-07-27 13:49 | 3 | Shannon Hastings | Justin Permar | 2009-07-27 13:49 | v1.3 | minor | None | Introduce | 1.4
22446 | Dorian appears to be publishing a CRL to GTS twice when a new account is created | 2009-07-23 13:43 | 2 | Stephen Langella | Scott Oster | 2009-07-23 13:43 | v1.3 | minor | None | Dorian | 1.3/1.4
22321 | The Transfer service intermittently and randomly loses callbacks on transfer contexts | 2009-07-14 21:08 | 3 | Shannon Hastings | Justin Permar | 2009-07-14 21:08 | v1.3 | critical | None | Transfer Service | 1.4
22308 | Introduce-generated services create EPRs with an incorrect hostname | 2009-07-14 18:05 | 3 | Shannon Hastings | Justin Permar | 2009-07-14 18:33 | v1.3 | critical | None | Introduce | 1.4
22275 | caGrid installer doesn't check Apache Tomcat version properly on Windows | 2009-07-09 19:42 | 3 | Shannon Hastings | Justin Permar | 2009-07-09 19:42 | v1.3 | None | None | Installer | 1.3/1.4
22096 | Introduce disallows hyphenated last names for Point of Contact | 2009-07-01 13:50 | 3 | Shannon Hastings | William Stephens | 2009-07-01 13:50 | v1.3 | normal | None | Introduce | 1.4
21065 | Infinite loop in Introduce updater | 2009-04-29 21:25 | 3 | Nobody | Justin Permar | 2009-04-29 21:25 | v1.3 | None | None | Introduce | 1.3/1.4
20794 | Introduce generates *-security-desc.xml files with inconsistent line breaks | 2009-04-17 12:32 | 3 | Nobody | Steve Lustbader | 2009-04-17 12:32 | v1.3 | minor | None | Introduce | 1.4 | ?
20775 | Websso configuration : websso-properties-template.xml | 2009-04-16 17:28 | 3 | Santhosh Garmilla | Santhosh Garmilla | 2009-04-16 17:28 | None | minor | None | WebSSO | 1.3/1.4
20774 | AuthenticationProviders urls may be null | 2009-04-16 17:26 | 3 | Santhosh Garmilla | Santhosh Garmilla | 2009-04-16 17:26 | None | minor | None | WebSSO | 1.3/1.4
20679 | Cannot select update patch after clicking &quot;Look for Updates&quot; for custom update site | 2009-04-13 18:13 | 4 | Shannon Hastings | William Stephens | 2009-04-13 18:13 | v1.3 | minor | None | Introduce | 1.3/1.4
20375 | Incorrect exception handling when deleting non-existant file | 2009-04-02 13:07 | 3 | Nobody | William Stephens | 2009-04-02 13:07 | v1.2 | normal | None | Transfer Service | 1.4
20196 | Installer overwrites the installed credentials if already installed credentials are selected | 2009-03-27 18:37 | 3 | Nobody | Joe George | 2009-03-27 18:41 | v1.3 | critical | Accepted As Bug | Installer | ?
20171 | websso packages sync description file | 2009-03-26 21:45 | 3 | Santhosh Garmilla | Manav Kher | 2009-03-26 21:45 | None | minor | None | WebSSO | 1.4
19306 | Introduce grid service path cannot contain spaces | 2009-02-10 21:33 | 4 | Shannon Hastings | Justin Permar | 2009-04-07 15:12 | v1.3 | major | None | Introduce | 1.4
19045 | Introduce generated WSDL breaks unique key contraint of WSDL XSD | 2009-01-30 01:41 | 4 | Shannon Hastings | Scott Oster | 2009-01-30 01:41 | v1.3 | major | None | Introduce | 1.4
18966 | JVM shutdown hooks sometimes don't run to completion under Tomcat | 2009-01-27 15:10 | 2 | Nobody | David Ervin | 2009-01-27 15:10 | None | minor | None | Other | 1.4 | ?
18649 | Certain types of Hibernate database tables for subclasses are not supported by Data Services with SDK 4.0 and 4.1 | 2009-01-06 15:01 | 3 | David Ervin | David Ervin | 2009-01-06 15:01 | None | None | Accepted As Bug | Data Services | ?
18252 | Introduce is not currently supporting GetCurrentMessage of the WS-Notification | 2008-12-09 17:03 | 3 | Nobody | Shannon Hastings | 2008-12-09 17:03 | HEAD | None | Accepted As Bug | Introduce | ?
17666 | Delegated Credential Types schema cannot be added to services via Introduce GUI | 2008-11-07 14:40 | 3 | Shannon Hastings | David Ervin | 2008-12-08 15:06 | v1.2 | None | Awaiting Response | Security | 1.4
16898 | Introduce creates cycles between sub-context's resource base and main service's config class | 2008-10-02 16:32 | 3 | Shannon Hastings | David Ervin | 2008-10-02 16:32 | v1.2 | None | None | Introduce | 1.4
16835 | Disable Index Service registeration options in Deployment Viewer when no metadata is present in service | 2008-09-30 13:44 | 2 | Shannon Hastings | Kevin Puscas | 2008-09-30 14:28 | v1.2 | minor | None | Introduce | 1.4
15611 | GAARDS generates error if certificate is not selected for viewing | 2008-07-29 16:45 | 3 | Nobody | Satish Patel | 2008-07-29 16:45 | None | minor | None | Other | 1.4
15609 | Multiple GAARDS documentation pages reference the &quot;ui&quot; target of projects which no longer exists | 2008-07-29 16:16 | 4 | Stephen Langella | Scott Oster | 2008-08-01 18:39 | v1.2 | normal | None | Documentation | 1.3/1.4
14007 | Multiple services using WS-Enumeration cannot run in same container | 2008-05-05 19:14 | 1 | David Ervin | David Ervin | 2008-12-05 21:15 | None | None | Accepted As Bug | Enumeration | 2
13529 | Spaces in GLOBUS_LOCATION or ANT_HOME causing errors on deployment for Introduce created services | 2008-04-08 15:14 | 3 | Shannon Hastings | Shannon Hastings | 2008-09-02 14:37 | None | None | None | Introduce | 1.4
12893 | Installer Error dialogs sometimes popup behind the installer itself, confusing the user | 2008-03-05 16:32 | 1 | Nobody | Scott Oster | 2008-03-05 16:32 | v1.2 | minor | Accepted As Bug | Installer | ?
12239 | Dorian should get authn service wsdl from build artifact | 2008-02-05 21:46 | 1 | Stephen Langella | Scott Oster | 2008-02-05 21:46 | v1.1 | None | None | Dorian | ?
11607 | DataService gets in inconsistent state and returns confusing errors when not properly initialized | 2008-01-15 15:19 | 3 | David Ervin | Scott Oster | 2008-01-15 15:19 | v1.1 | normal | None | Data Services | 2.0/?
9466 | Introduce is not passing any system properties on to it's ant calls it makes when running the engine. | 2007-10-15 13:18 | 3 | Shannon Hastings | Shannon Hastings | 2007-10-15 13:18 | HEAD | normal | None | Introduce | 1.4
8146 | 2 &gt;= 2 error in GridGrouper my groups | 2007-08-02 13:35 | 1 | Stephen Langella | Scott Oster | 2008-12-07 01:19 | v1.1 | minor | Accepted As Bug | Grid Grouper | ?
7671 | Lowercase chars in complexType names from schema can cause compile failure | 2007-06-29 20:03 | 1 | David Ervin | David Ervin | 2008-12-05 21:16 | None | None | Accepted As Bug | Data Services | 2