## general_report
CITIH - Center for IT Innovations in Healthcare
Displaying 78 issues at 02/May/11 3:03 PM.
Key | Priority | Created | Summary | Original Estimate | Fix Version/s | Description
CAGRID-90 | Major | 2009-10-09 12:51 | Migrate the from XMI datatype browser to SDK 4.3 (or newer) | 144000 | caGrid 1.5
CAGRID-103 | Major | 2009-10-09 16:43 | Investigate feasibility/impact of JBoss 5.1.x as a deployment container | 28800 | caGrid 1.5
CAGRID-104 | Major | 2009-10-09 16:43 | Investigate feasibility/impact of Tomcat 6.0.x as a deployment container | 288000 | Sprint-2009-3 caGrid 1.4 caGrid 1.4 SHA2 caGrid 1.5
CAGRID-107 | Major | 2009-10-09 16:47 | CAGRID-83 Unify use of Spring to version 2.5.6 | 57600 | caGrid 1.5
CAGRID-108 | Major | 2009-10-09 16:47 | CAGRID-83 Investigate feasibility/impact of MySQL 5.1.x | 28800 | caGrid 1.5
CAGRID-110 | Minor | 2009-10-12 14:45 | Migrate containers in integration-tests to targeted tech stack | 144000 | caGrid 1.5
CAGRID-161 | Minor | 2009-11-10 08:45 | Fix issues with system build when directory paths have spaces in them | 288000 | caGrid 1.5
CAGRID-173 | Trivial | 2009-11-20 11:20 | Breakup the ws-core ivy module to have finer grain configurations | 3600 | caGrid 1.5 | things like the testing/samples shouldn't be needed for a minimal conf
CAGRID-357 | Trivial | 2010-03-17 13:33 | Provide Mechanism for Dorian users to reset their password if they forget it. | 144000 | caGrid 1.5
CAGRID-372 | Major | 2010-04-15 09:52 | caGrid build to support Ant 1.8 | 28800 | caGrid 1.5 | The proposed NCICB tech stack calls for Ant 1.8. It's a good idea to move forward anyway, since ant 1.7 is aging and 1.8 brings numerous improvements. Currently, building with ant 1.8 fails: http://quality.cagrid.org/job/caGrid-Continuous-BuildOnly-Ant_1.8/ It's also important to note that Introduce generated services won't build with ant 1.8 due to a forward classpath reference issue. This is easy to rectify (one liner in the build.xml), but the 1.4 upgraders will need to make the change as well.
CAGRID-380 | Minor | 2010-04-19 15:59 | Additional service resource property on caGrid services to indicate "annotation source" | 57600 | caGrid 1.5 | caGrid services need an additional resource property to indicate their "semantic annotation source' to provide some context for where CDEs and concept codes utilized in the service metadata / domain model came from. With the upcoming deprecation of caDSR, we need a way to identify what the authoritative source for semantic information is.
CAGRID-393 | Trivial | 2010-05-11 15:15 | Introduce deployment GUI to have "advanced option" to turn off deployment validation | 14400 | caGrid 1.5 | Introduce's service deployment GUI ought to have a way to deploy for testing that doesn't require filling in the service metadata. Similar to the command line ant deployTomcat -Dno.deployment.validation=true. Ditto for index service registration.
CAGRID-413 | Blocker | 2010-06-16 14:25 | Create caGrid 1.4 release |  | caGrid 1.4 | Cut the 1.4 release
CAGRID-429 | Critical | 2010-07-07 10:37 | Documentation complete |  | caGrid 1.4
CAGRID-431 | Critical | 2010-07-07 10:40 | NCI Production Grid upgrade complete |  | caGrid 1.4
CAGRID-433 | Major | 2010-07-07 14:29 | Finalize caGrid 1.4 documentation |  | caGrid 1.4 | caGrid Task Linked to task in caGrid for quick reference in meetings.
CAGRID-466 | Trivial | 2010-08-02 16:01 | Move symlink on software.cagrid.org for "repository" |  | caGrid 1.4 Sprint 2011_04_25-2011_05_06 | When the release announcement is made, move the symlink in ~cagrid/public_html for "repository" from 1.3 to 1.4
CAGRID-470 | Major | 2010-08-06 14:15 | Inconsistent user and host search operation behavior | 86400 | caGrid 1.5 | Dorian 1.4 added two new operations (userSearch and hostSearch) to allow non-admin users the ability to perform those type of functions. For 1.4, GAARDS was updated to use the new search functionality in several areas (grid grouper, cds. gts) but not on the screens reached from the "Account Management" menu. If a non-admin user attempts to use the management screens to search for a host or user they will still receive the "You are NOT an Administrator!!!" error. This is an inconsistent presentation to the user for the search functionality. The user will be required to remember what screens they can and cannot search from. GAARDS should be updated to have the same behavior on all search screens.
CAGRID-482 | Trivial | 2010-08-20 11:38 | Update Identifiers NamingAuthority na.properties file URLs to be configured by "ant configure" | 3600 | caGrid 1.4 caGrid 1.4 SHA2 caGrid 1.5 Sprint 2011_04_25-2011_05_06 | https://ncisvn.nci.nih.gov/svn/cagrid/branches/caGrid-1_4_release/Software/core/caGrid/projects/identifiers-namingauthority/WebContent/WEB-INF/na.properties cagrid.na.prefix=https://140.254.126.79:8443/osumc/ssl/ cagrid.na.schemauri=https://localhost:8444/namingauthority/org.cagrid.identifiers.namingauthority.xsd cagrid.na.grid.url=https://localhost:8443/wsrf/services/cagrid/IdentifiersNAService https://ncisvn.nci.nih.gov/svn/cagrid/branches/caGrid-1_4_release/Software/core/caGrid/projects/identifiers-namingauthority-gridsvc/etc/na.properties cagrid.na.prefix=https://localhost:8444/namingauthority/NamingAuthorityService/ cagrid.na.grid.url=http://localhost:8081/wsrf/services/cagrid/IdentifiersNAService
CAGRID-494 | Minor | 2010-09-10 11:58 | Define all needed grid service URLs in the target grid serviceURLs.properties file | 14400 | caGrid 1.5 | The current serviceURLs.properties file only contains a few of the core grid service URLs for a grid. We should consider updating this to allow additional projects, like identifiers, to be automatically configure with the correct URLs for a grid.
CAGRID-500 | Trivial | 2010-10-06 10:54 | Update caGrid timeline png and vsd | 600 | caGrid 1.4 | The 1.4 release looks to be in the 21st century. The PNG and VSD versions need updated in both the trunk and the 1.4 branch
CAGRID-505 | Minor | 2010-10-21 12:03 | Investigate use of Mozilla Rhino Javascript engine to parse PAC files | 14400 | caGrid 1.4 SHA2 caGrid 1.5 | Since Proxy Auto-Conf (PAC) files are Javascript that implement the "FindProxyForURL(url, host)" method, it *might* be possible to use Mozilla's Rhino JS parsing engine to read the PAC file and configure proxy connections on the fly. http://www.mozilla.org/rhino/
CAGRID-530 | Major | 2010-11-15 13:55 | Create Tomcat 6 container for testing | 7200 | caGrid 1.4 SHA2 caGrid 1.5
CAGRID-537 | Major | 2010-11-16 09:14 | Support caCORE SDK 4.4 |  | caGrid 1.5 | Satish claims it's identical to 4.3 with some bugfixes, etc. We'll see.
CAGRID-538 | Trivial | 2010-11-16 09:23 | Fix taverna workflow service project to work with single project build | 1800 | caGrid 1.5 | The taverna workflow service can't be built from the top level of cagrid using the single project build command. ant build-project -Dsingle.project.name=TavernaWorkflowService should work; it doesn't.
CAGRID-540 | Critical | 2010-11-18 13:26 | SHA-2 support | 2880000 | caGrid 1.4 SHA2 | A NIST mandate indicates that Federal systems should be using SHA-2 signatures and certs by the end of the year. LOTS of investigation and redevelopment needs to happen to make this work in caGrid security services and clients to the same. http://csrc.nist.gov/publications/PubsDrafts.html#SP-800-131
CAGRID-544 | Trivial | 2010-11-18 14:02 | CAGRID-540 Decide on content of, write and send communiqué to users regarding legacy use of SHA-1 | 28800 | caGrid 1.4 SHA2
CAGRID-561 | Trivial | 2010-12-07 13:20 | CAGRID-413 Upload GAARDS standalone zip to software.cagrid.org | 3600 | caGrid 1.4 | The GAARDS Standalone zip is linked to on this page: https://cagrid.org/display/gaardsui14/Downloads The zip on software.cagrid.org needs to be updated with the actual release version at release: http://software.cagrid.org/gaards/1.4/gaards-ui-1.4-bin.zip
CAGRID-562 | Major | 2010-12-07 14:12 | A way to add new target grids to the top-level configure target | 28800 | caGrid 1.5 | We need a way to add new target grid ivy repositories to the top-level 'configure' target. Currently, adding a new target grid from a remote repository involves editing the master ivysettings.xml file and running configure-clean to see the new grid configuration before you can run ant configure -Dtarget.grid=my-grid-here
CAGRID-603 | Minor | 2011-01-24 22:33 | Update XML API used to parse SAML assertions in opensaml project | 144000 | caGrid 1.4 caGrid 1.5 | caGrid currently uses XML APIs that have never been updated via the xmi-apis.jar (endorsed jar). This causes significant jar conflict issue when someone attempts to perform grid user authentication in a web framework that uses a modern XML parser. example exception from user attempting to use Grails (empty project with endorsed jars copied into the lib directory): java.lang.LinkageError: Class org/xml/sax/SAXParseException violates loader constraints at java.lang.Class.getDeclaredMethods0(Native Method) at java.lang.Class.privateGetDeclaredMethods(Class.java:2395) at java.lang.Class.getDeclaredMethods(Class.java:1763) at java.security.AccessController.doPrivileged(Native Method) at org.codehaus.groovy.util.LazyReference.getLocked(LazyReference.java:46) at org.codehaus.groovy.util.LazyReference.get(LazyReference.java:33) at grails.util.PluginBuildSettings.getPluginInfos(PluginBuildSettings.groovy:121) at grails.util.PluginBuildSettings.getPluginInfos(PluginBuildSettings.groovy) at grails.util.PluginBuildSettings$getPluginInfos.callCurrent(Unknown Source) at grails.util.PluginBuildSettings.getPluginInfo(PluginBuildSettings.groovy:164) at grails.util.PluginBuildSettings$getPluginInfo.callCurrent(Unknown Source) at grails.util.PluginBuildSettings.getPluginInfoForSource(PluginBuildSettings.groovy:205) at org.codehaus.groovy.transform.ASTTransformationVisitor$3.call(ASTTransformationVisitor.java:302) at org.codehaus.groovy.control.CompilationUnit.applyToSourceUnits(CompilationUnit.java:814) at org.codehaus.groovy.control.CompilationUnit.doPhaseOperation(CompilationUnit.java:511) at org.codehaus.groovy.control.CompilationUnit.processPhaseOperations(CompilationUnit.java:487) at org.codehaus.groovy.control.CompilationUnit.compile(CompilationUnit.java:464) at _GrailsEvents_groovy.run(_GrailsEvents_groovy:54) at _GrailsEvents_groovy$run.call(Unknown Source) at _GrailsClean_groovy$run.call(Unknown Source) at _GrailsClean_groovy.run(_GrailsClean_groovy:29) at _GrailsClean_groovy$run.call(Unknown Source) at _GrailsWar_groovy$run.call(Unknown Source) at _GrailsWar_groovy.run(_GrailsWar_groovy:34) at _GrailsWar_groovy$run.call(Unknown Source) at War.run(War.groovy:29) at War$run.call(Unknown Source) at gant.Gant.prepareTargets(Gant.groovy:606)
CAGRID-618 | Trivial | 2011-02-04 11:11 | CAGRID-603 Need some unit tests in the openSAML project to verify this still works. |  | caGrid 1.5
CAGRID-619 | Minor | 2011-02-08 10:35 | Client side utility to get the host identity of a grid service | 28800 | caGrid 1.4 SHA2 caGrid 1.5 | We need a client-side tool that can figure out the grid identity of a secure grid service. Once we get this, it'll be much easier for clients to delegate credentials with CDS, since you must know the identity of the service you want to delegate to.
CAGRID-631 | Critical | 2011-02-17 15:33 | GRAPE framework needs to know where to load extension classes from | 7200 | caGrid 1.5 Sprint 2011_04_25-2011_05_06 | It would seem that in the process of fixing up Introduce's long classpath vs windows issue, I made it so that Grape (the MDI window framework we're using) can't find the extension classes for the buttons we add to the toolbar at the top.
CAGRID-646 | Major | 2011-03-29 12:21 | FQP performance and scalability enhancements | 288000 | caGrid 1.5 | FQP should look at incorporating and improving on the changes UAB made to let FQP scale to large query results
CAGRID-655 | Major | 2011-04-07 16:23 | caCore SDK 4.x data service styles need upgraders to handle swapping out Spring versions for SHA2 support | 28800 | caGrid 1.4 SHA2 Sprint 2011_04_25-2011_05_06 | We need to replace the Spring jar used by the SDK backed data services with a newer version. if this is a simple 1:1 drop-in, this task should be quick. If it introduces issues for the SDK, this will take a long time to get right.
CAGRID-666 | Major | 2011-04-26 15:17 | CAGRID-537 Back-port the style to caGrid / introduce 1.3 | 28800 | caGrid 1.5 | The style needs backported to caGrid / Introduce 1.3. This means we need to get rid of the CQL 2 query processor and just use CQL 1. The obvious caveat here is that the SDK suffers from bug #31022 (https://gforge.nci.nih.gov/tracker/index.php?func=detail&aid=31022&group_id=148&atid=730). For that reason, this task is currently unscheduled.
CAGRID-673 | Major | 2011-04-29 09:33 | CAGRID-652 Figure out at what point the SDK data service is failing to serialize results | 28800 | General Investigation caGrid 1.5 | The data services backed by caCORE SDK don't return any results when run inside an openJDK VM. Figure out at what point the results go away. Possible culprits: Castor [de]serialization Hibernate CGLib proxy Spring
CAGRID-677 | Minor | 2011-05-02 14:59 | CAGRID-173 Fix projects in caGrid to use WS-Core artifacts from Ivy rather than relying on GLOBUS_LOCATION | 86400 | caGrid 1.5
Generated at Mon May 02 15:03:48 EDT 2011 by David Ervin using JIRA 4.1.2#531.